🚀 DIVERSE DIGITAL — 90-DAY RELAUNCH PLAN

🔥 PHASE 1: Foundation & Visibility (Days 1–30)

Goal: Build strong brand foundations + create awareness of the relaunch.

WEEK 1 — Brand Finalisation

- Finalise new brand messaging

- Update bio + descriptions across all platforms

- Design new branded templates (Canva)

- Upload new profile images and headers

- Create a “New Diverse Digital” highlight on Instagram

Deliverables:
✔ Website copy drafted
✔ Service packages finalised
✔ Launch announcement prepared

WEEK 2 — Website & Portfolio

- Build/refine your website (or one-page landing site to start)

- Create a portfolio page with:

  - Previous content samples

  - Testimonials

  - Case studies (even brief ones)

- Create downloadable Service Brochure PDF

- Set up a lead capture form (“Join the mailing list for digital tips”)

Deliverables:
✔ Functional landing page
✔ Portfolio ready for prospects

WEEK 3 — Social Media Relaunch

- Post the official relaunch announcement

- Begin a 3-post/week schedule:

  - Value post (digital tips)

  - Visibility post (your story/mission)

  - Promo post (service spotlight)

- Create a 30-day content calendar

- Record 3–5 short intro videos (who you help & how)

Deliverables:
✔ Relaunch content live
✔ Content plan for the month

WEEK 4 — Networking & Outreach

- Reconnect with previous clients

- Message LinkedIn contacts with the new offer

- Join groups: Black entrepreneurs, Deaf entrepreneurs, CIC owners, purpose-led founders

- Post an offer: “5 discounted strategy sessions for relaunch month.”

- Email your list announcing the relaunch

Deliverables:
✔ 10–20 personalised outreach messages
✔ 5–10 discovery calls booked

🔥 PHASE 2: Growth & Lead Generation (Days 31–60)

Goal: Build consistent visibility + attract steady enquiries.

WEEK 5 — Thought Leadership Push

- Publish 1 long-form LinkedIn post or article

- Share a case study on social media

- Create a carousel: “Who the new Diverse Digital supports”

- Start a weekly educational series:

  - “Digital Confidence Tips”

  - “Marketing Made Simple”

  - “Inclusive Communication 101”

Deliverables:
✔ Regular long-form content
✔ Becoming known for your niche

WEEK 6 — Workshops & Free Value

Run one of the following (online):

- “How to Improve Your Digital Visibility in 2025”

- “Accessible Communications for Small Organisations”

- “Create Your 30-Day Content Plan (Live)”

Promote it across all channels.
Use Eventbrite + LinkedIn events.

Deliverables:
✔ A free workshop attracting 20–60 sign-ups
✔ Grow email list

WEEK 7 — Partnerships

Begin securing visibility collaborations with:

- Deaf business organisations

- Women of Colour business networks

- CIC communities

- Small business support hubs

- Black and Asian business networks

Offer:
Free guest talk / Q&A / digital skills session
in exchange for:

- Email list promotion

- Social media recognition

- Being featured on their channels

Deliverables:
✔ 3–5 partnership confirmations

WEEK 8 — Relaunch Promo Offer

Promote one of these:

- 10% off social media packages

- £99 digital audit

- £49 mini content strategy session

- Free consultation for CICs

Deliverables:
✔ Enquiries increase
✔ Convert 2–4 paying clients

🔥 PHASE 3: Conversion & Expansion (Days 61–90)

Goal: Convert leads, secure long-term clients, and build authority.

WEEK 9 — Showcase Real Client Work

- Share before/after examples

- Share “What I did for this client” reels or carousels

- Upload testimonials

- Ask 3 existing clients for case studies

- Share behind-the-scenes: content planning, editing, strategy work

Deliverables:
✔ Portfolio strengthened
✔ Boost in credibility

WEEK 10 — Optimise Your Offers

Review:

- What services are people asking for?

- Which enquiries are most profitable?

- Which package needs adjusting?

Then:

- Create one new mid-tier package

- Update website copy

- Improve onboarding system (i.e., contracts, Wix forms, Stripe payments)

Deliverables:
✔ Clear, simplified services
✔ Smoother onboarding

WEEK 11 — Paid or Bigger Visibility

Choose one:

- Small £20–£50 Instagram ad

- LinkedIn promotional post

- Guest appearance on a podcast

- Write an article for a community business platform

Deliverables:
✔ Bigger audience reach
✔ Strong new visibility channels

WEEK 12 — Review & Scale

Review the past 90 days:

- How many enquiries?

- How many clients?

- What content performed well?

- What partnerships helped?

- What needs to stop / start / continue?

Then set your long-term strategy for the next 6 months, including:

- Building an email newsletter

- Creating a low-ticket product (e.g., £9–£27 content templates)

- Scaling your coaching program

- Hiring a VA or part-time support

Deliverables:
✔ 6-month growth plan
✔ Stable client base
✔ Clear brand reputation

⭐ 90-Day Key Targets

By the end of 90 days, you should realistically achieve:

✔ 6–12 discovery calls

✔ 3–6 new monthly retainer clients

✔ 200–500 new followers across platforms

✔ At least 1 partnership collaboration

✔ 1–2 strong case studies

✔ A fully functioning digital presence

Want me to create next?

I can prepare:
📌 A downloadable 90-day plan (PDF)
📌 A 30-day content plan for the relaunch
📌 Email sequences for the relaunch
📌 Outreach message templates
📌 Website copy for all pages